## Daily Report
CONSTRUCTION DAILY REPORT
Company name · logo · phone · email
1. Report details
Project name |  |  | Project address
Report date |  |  | Report no.
Prepared by |  |  | Role
Site hours (start – end) |  |  | Client / owner
2. Weather
Conditions |  |  | Temp (high / low)
Wind |  |  | Humidity
Weather impact on work (what stopped, from – to)
3. Work performed
Work performed today (what, where, by whom)
Locations / zones
Subcontractors on site
Planned for tomorrow
4. Labor / manpower
Trade | Company | Workers | Hours each | Total hours | Notes
Totals
5. Equipment
Equipment | Qty | Hours used | Idle hours | Notes
Totals
6. Materials & deliveries
Material | Quantity | Supplier | Received by | Location / condition
7. Delays & issues
Type | Description | Time lost (hrs) | Cause / responsible party | Photos?
Totals
8. Safety
Toolbox talk held? (topic)
PPE compliance
Incidents / near misses
Inspections / visitors
9. Photos taken today
# | Time | Location | Category (progress / issue / safety / delivery) | Description
10. Final notes & sign-off
Notes / next steps:
Prepared by (name, signature, time)
Reviewed by (name, signature, time)
Template by Daily Site Log — dailysitelog.com/blog/construction-daily-report-template. Free to use and modify.

## Delay types
Type | Record this
Weather | Conditions, start/stop times, which activities stopped, weather source (app screenshot or station).
Material | What was late, supplier, PO/delivery ref, promised vs actual date, crews idled.
Labor shortage | Trade short, headcount planned vs actual, who was notified.
Equipment breakdown | Machine, failure, downtime hours, replacement arranged.
Client decision pending | Decision needed, date requested, who owns it, work blocked.
Drawing / RFI issue | Drawing/RFI number, date raised, what cannot proceed.
Subcontractor | Sub name, scope affected, notice given (time, method).
Inspection | Inspection type, scheduled vs actual, authority, result.
Safety | Incident/near miss, stop-work time, corrective action.
Site access | Cause (permits, neighbours, road closure), duration.
Other | Anything else — be specific about time lost and cause.