## Delay log
Construction delay log
Project: |  | Contract no.: |  |  | Prepared by:
One row per delay event. Fill it the same day, keep it updated until the delay ends, and cite the daily report and photos for each row.
# | Date started | Delay type | What happened (facts only) | Start time | End time / ongoing | Hours lost | Activities affected | On critical path? | Crew & equipment idle | Caused by (party) | Excusable? | Compensable? | Notice sent (date & ref) | Evidence (report ID, photos) | Mitigation taken | Status
1 | 2026-10-14 | Material delivery | EXAMPLE (delete this row): Ready-mix truck arrived 3 h late; pour of footings A-C could not start. Crew and pump on standby. | 7:00 | 10:00 |  | Footing pour gridlines A-C | Yes | 6 concrete workers, 1 pump + operator | Ready-mix supplier | Yes | Check contract | 2026-10-14, email ref D-03 | DCL-2026-MY3DVBSG, 2 photos | Crew moved to formwork prep at 08:30 | Closed
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45
46
47
48
49
50
51
52
53
54
55
56
57
58
59
60
Total hours lost

## How to use
How to keep a delay log that holds up
1. One row per delay event, started the same day it happens.
2. Facts only: times, quantities, names. Leave opinions and blame out of the description; record the party in its own column.
3. If the delay is still going at the end of the day, write 'ongoing' and update the row daily until it ends.
4. Link each row to that day's daily report and photos. The log is the index; the daily reports are the evidence.
5. Record notice: the date you notified the other party and the reference. Many contracts bar late claims (often 7 to 28 days).
6. 'Excusable' means you may be entitled to more time; 'compensable' means you may also be entitled to money. Your contract decides.
General guidance, not legal advice. Free template from dailysitelog.com. Daily Site Log keeps this log automatically from your daily reports.