[Contractor letterhead]

[Date]

[Owner / Employer / Contract Administrator name]
[Address]
[Email per contract notice clause]

By [email / hand / recorded post — the method your contract specifies]

Re: [Project name] — Contract No. [__] — Notice of delay: adverse weather

Dear [Name],

1. Notice. In accordance with clause [__] of the Contract, we give notice of a delay event affecting the Works.

2. Event. Between [date] and [date / ongoing], the site experienced [describe: rainfall of __ mm / sustained winds of __ / temperatures below __ °C], recorded by [weather station / site gauge]. In our assessment these conditions were exceptionally adverse for the location and season and could not reasonably have been anticipated.

3. Effect. The conditions prevented or slowed the following activities: [list activities, locations, and dates]. [State whether critical.] Details, including times, crews and equipment affected, and photographs, are recorded in Daily Reports Nos. [__] to [__], copies of which are available on request / attached.

4. Status. The event is [ongoing / ended on (date)]. Ground and access conditions [remain / are expected to remain] unworkable for [activities] until approximately [date].

5. Mitigation. We have [resequenced work to interior areas / deployed pumps and covers / offered weekend working / other] to reduce the effect on the programme.

6. Reservation of rights. We will submit particulars of the delay, including a revised programme and the extension of time claimed [and any associated cost where the Contract provides for recovery], within the period required by clause [__]. This notice is given without prejudice to our rights under the Contract and at law.

7. Request. Please acknowledge receipt of this notice. [If applicable: We also require your instruction / decision on [item] by [date] to avoid further delay.]

Yours faithfully,

[Name]
[Title, per contract]
[Contractor]
[Phone / email]

cc: [Architect / Engineer / Project Manager, as required by the contract]

Daily Site Log — dailysitelog.com. Free to use and modify. General information, not legal advice.